## Architecture Governance
Stage | Decision Description | Business Driver | Options Considered | Chosen Option | Trade-Off Accepted | Risk Level (Low/Med/High) | Risk Mitigation Plan | Owner (RACI - Accountable) | Review Date | KPIs Impacted | ADR Reference Link
Architecture Style | Select initial architecture for Claims Processing System | Faster time-to-market | Monolith ¦ Modular Monolith ¦ Microservices | Modular Monolith | Reduced independent scaling early-stage | Medium | Reassess at 5x traffic growth | Chief Architect | Quarterly | Deployment Frequency, MTTR | ADR-001
Data Architecture | Primary transactional data store selection | Strong consistency for financial records | SQL ¦ NoSQL ¦ Polyglot | SQL | Horizontal scaling complexity | Medium | Introduce read replicas and partitioning | Data Architect | Bi-Annual | Latency, Error Rate | ADR-002

## Risk Register
Risk ID | Category (Tech/Business/Ops) | Risk Description | Probability (1-5) | Impact (1-5) | Risk Score (P x I) | Mitigation Strategy | Contingency Plan | Owner
R-001 | Technical | Traffic spike causing service outage | 4 | 5 |  | Auto-scale + Load testing | Activate DR region | SRE Lead

## Azure Mapping
Architecture Concern | Azure Service | Purpose | HA Strategy | Cost Optimization Strategy | Monitoring Tool
API Gateway | Azure API Management | Centralized API control | Multi-region deployment | Consumption tier for low traffic | Application Insights
Compute | Azure App Service / AKS | Microservices hosting | Auto-scale rules | Reserved instances | Azure Monitor
Messaging | Azure Service Bus | Async communication | Geo-disaster recovery | Standard tier where possible | Azure Monitor
Database | Azure SQL / Cosmos DB | Transactional storage | Geo-replication | Autoscale / DTU optimization | SQL Insights
Identity | Azure AD B2C | Authentication & Authorization | Multi-region config | Right-size tenant configuration | Azure AD Logs

## KPI & SLA Tracker
Metric Name | Target SLA | Current Value | Threshold Alert | Business Impact | Owner
API Availability | 99.9% |  | Below 99.5% | Revenue impact | SRE Team
P95 Latency | < 300 ms |  | Above 400 ms | Poor UX | Platform Team
Error Rate | < 1% |  | Above 2% | Customer complaints | Engineering Lead

## Review Checklist
Category | Checklist Item | Status (Yes/No) | Comments
Security | Are all APIs protected with AuthN/AuthZ?
Resilience | Are retries and circuit breakers implemented?
Scalability | Is autoscaling tested under load?
Observability | Are logs, metrics, and traces centralized?
Cost | Is monthly cloud spend within budget forecast?
Compliance | Is audit logging enabled?