## Cloud-Migration on Azure
Phase | Step | What | Why | Actions/Notes
1 — Foundation | 1.1 | Azure Tenant | Org identity boundary; everything lives here | Verify Tenant ID in Entra ID
1 — Foundation | 1.2 | Management Groups | Policies/RBAC cascade down | Create MGs in Azure Portal
1 — Foundation | 1.3 | Subscriptions | Blast radius isolation; cost tracking | Separate subs for connectivity, mgmt, nonprod, prod
1 — Foundation | 1.4 | Naming Convention | Cannot rename most resources | Define/document before creating anything
1 — Foundation | 1.5 | Tagging Strategy | Cost mgmt, ownership clarity | Enforce via Policy
1 — Foundation | 1.6 | Resource Groups | Logical containers per concern | rg-network-prod-eastus, rg-compute-prod-eastus etc.
2 — Networking | 2.1 | Plan IP Space | VNets cannot overlap; AKS needs large subnet | Hub VNet 10.0.0.0/16; Prod Spoke 10.1.0.0/16 etc.
2 — Networking | 2.2 | Create VNets + Peering | Hub-spoke topology | Hub VNet, Prod Spoke, Dev Spoke, peer them
2 — Networking | 2.3 | NSGs | Deny all inbound; allow only required | Attach NSG per subnet
2 — Networking | 2.4 | Private DNS Zones | Needed before private endpoints | privatelink.database.windows.net etc.
2 — Networking | 2.5 | Firewall/NVA | Outbound control | Deploy Azure Firewall in Hub VNet
3 — Identity | 3.1 | Human Access | RBAC for team members | Assign roles at MG/Subscription level
3 — Identity | 3.2 | Service Identities | Managed Identities for services | Prefer User-Assigned
3 — Identity | 3.3 | Workload Identity | AKS pods federated to Managed Identity | Enable OIDC issuer
3 — Identity | 3.4 | Pipeline Identity | CI/CD identity with least privilege | Federate GitHub/ADO to Azure
4 — Security Baseline | 4.1 | Key Vault | Secrets storage | Enable purge protection, RBAC, private endpoint
4 — Security Baseline | 4.2 | Defender | Threat detection | Enable Defender plans
4 — Security Baseline | 4.3 | Azure Policy | Governance enforcement | Assign initiatives at MG level
5 — Registry & CI/CD | 5.1 | ACR | Image storage | Premium SKU, private endpoint, attach to AKS
5 — Registry & CI/CD | 5.2 | Source Repo | Code + infra separation | /src, /infra, /k8s, /tests
5 — Registry & CI/CD | 5.3 | CI Pipeline | Build/test/scan/push | PR + main triggers
5 — Registry & CI/CD | 5.4 | IaC Pipeline | Infra deployment | Validate, plan, approval, apply
6 — Compute | 6.1 | Decision | Choose AKS, Functions, Container Apps, App Service | Based on workload type
6 — Compute | 6.2a | AKS | Cluster setup | Private, OIDC, add-ons, namespaces, quotas
6 — Compute | 6.2b | Functions | Function App | Premium plan, VNet integration, Key Vault references
6 — Compute | 6.2c | Container Apps | Environment + apps | Managed Identity, KEDA scaling
7 — Data Layer | 7.1 | Azure SQL | Relational DB | AAD auth only, private endpoint, RBAC access
7 — Data Layer | 7.2 | Cosmos DB | NoSQL | Partition key design, private endpoint, RBAC
7 — Data Layer | 7.3 | Redis | Cache | Premium tier, private endpoint, Entra ID auth
7 — Data Layer | 7.4 | Storage | Blob/Queue/Table | Disable public access, enable soft delete, RBAC
8 — Messaging | 8.1 | Service Bus | Async backbone | Premium tier, private endpoint, topics/queues, DLQ
8 — Messaging | 8.2 | Event Hubs | Streaming telemetry | Partitions, consumer groups, RBAC
9 — API Gateway | 9.1 | APIM | Front door for APIs | Premium tier, VNet mode, import OpenAPI specs
9 — API Gateway | 9.2 | Front Door/WAF | Global edge | TLS enforcement, WAF policies
10 — Observability | 10.1 | Log Analytics/App Insights | Monitoring | Alerts before prod traffic, go-live checklist

## Azure Cross-Skilling Program (T
Session # | Title | Week | Pillar | Learning Objectives | Breakdown | Demo/Concept | Homework
1 | Azure 101 — Mental Model | 1 | Foundation | Understand Azure basics; Portal; CLI | 0–5 Intro; 5–15 Concept; 15–35 Deep Dive; 35–45 Demo; 45–55 Discussion; 55–60 Homework | Portal walkthrough; CLI commands | Create free Azure account; RG screenshot
2 | Azure Organization — Tenants & Subs | 1 | Foundation | Understand hierarchy Tenant→MG→Subs→RG | 0–5 Recap; 5–20 Concept; 20–40 Deep Dive; 40–50 Demo; 50–60 Q&A | Portal hierarchy; CLI tagging | Map actual subscription structure
3 | Azure Networking — VNets/Subnets/NSG | 1 | Networking | Understand VNet, Subnet, NSG, Private Endpoint | 0–5 Recap; 5–20 Concept; 20–40 Deep Dive; 40–50 Demo; 50–60 Q&A | CLI create VNet/Subnet/NSG | Diagram current network or describe SQL without private endpoint
4 | Identity in Azure — Entra ID & RBAC | 1 | Identity | Understand human vs service identity; RBAC; Managed Identity | 0–5 Recap; 5–20 Concept; 20–40 Deep Dive; 40–50 Demo; 50–60 Q&A | Create Managed Identity; assign RBAC | Audit credentials in service; plan migration to MSI
5 | Azure Key Vault — Secrets & Config | 1 | Security | Understand Key Vault; how to use in .NET; references in App Service/AKS | 0–5 Recap; 5–15 Concept; 15–35 Deep Dive; 35–50 Demo; 50–60 Q&A | Create KV; store secret; read via SDK | Audit service secrets; plan migration to KV
6 | Azure App Service — Deploy .NET API | 2 | Compute | Understand App Service; deploy API; slots | 0–5 Recap; 5–15 Concept; 15–35 Deep Dive; 35–50 Demo; 50–60 Q&A | CLI deploy API; GitHub Actions | Deploy sample API to App Service
7 | Azure Container Apps — Simplified Containers | 2 | Compute | Understand Container Apps; when to use | 0–5 Recap; 5–15 Concept; 15–35 Deep Dive; 35–50 Demo; 50–60 Q&A | Portal/CLI create Container App | Deploy sample container
8 | AKS Part 1 — Cluster Setup | 2 | Compute | Understand AKS basics; cluster creation | 0–5 Recap; 5–15 Concept; 15–35 Deep Dive; 35–50 Demo; 50–60 Q&A | CLI create AKS cluster | Deploy sample workload
9 | AKS Part 2 — Networking/Security | 2 | Compute | Understand AKS networking, scaling, security | 0–5 Recap; 5–15 Concept; 15–35 Deep Dive; 35–50 Demo; 50–60 Q&A | Configure ingress, HPA, Network Policies | Secure AKS workload
10 | Azure Functions — Serverless | 2 | Compute | Understand Functions; triggers; serverless | 0–5 Recap; 5–15 Concept; 15–35 Deep Dive; 35–50 Demo; 50–60 Q&A | Create Function App; trigger demo | Deploy sample function
11 | Azure SQL Database | 3 | Data | Understand managed relational DB | Concept + Demo | Create SQL DB; connect via MSI | Homework: provision DB
12 | Azure Cosmos DB | 3 | Data | Understand NoSQL; partition keys | Concept + Demo | Create Cosmos DB; private endpoint | Homework: design partition key
13 | Azure Cache for Redis | 3 | Data | Understand caching patterns | Concept + Demo | Create Redis; configure eviction | Homework: implement caching
14 | Azure Blob Storage | 3 | Data | Understand blob storage; lifecycle | Concept + Demo | Create Storage Account; upload blob | Homework: configure lifecycle
15 | Azure Service Bus | 4 | Messaging | Understand async messaging | Concept + Demo | Create Service Bus; topic/queue | Homework: send/receive message
16 | Azure Event Hubs | 4 | Messaging | Understand event streaming | Concept + Demo | Create Event Hub; consumer group | Homework: stream telemetry
17 | Azure Event Grid | 4 | Messaging | Understand cloud events | Concept + Demo | Create Event Grid; subscription | Homework: publish event
18 | API Management (APIM) | 4 | Integration | Understand API gateway | Concept + Demo | Create APIM; import OpenAPI | Homework: expose API
19 | Azure Front Door & WAF | 4 | Integration | Understand edge/CDN/security | Concept + Demo | Create Front Door